## Index
Sheet types
|  |  | / DRAFT | Input: Facts
Input: Assumptions
Calculation
Output
OppCat Architecture Assessment Tracker
Last changed on: 29-Jul-2026
Requirement-by-requirement responses against the Architecture Assessment framework (180 requirements).
| Sheet Name | Description | Type
8TXtzVME | Tracker | Full 180-requirement status: original and proposed priority, classification, responses, status, owner, technical comment, and recommended action. | Output
C9TY6N0M | Summary | Counts of status by area and by owner, plus MUST-coverage KPIs (formula-driven). | Output
QzffmkCa | Action Items | Discussion points, disagreements needing resolution, suggested next steps. | Output

## Tracker
OppCat Architecture Assessment Tracker
Sheet "Tracker"
Last changed on: 22-Sept-2026 |  |  |  | / DRAFT
ARC v2 — Architecture Assessment Response Tracker
Status = reviewer derivation from responses. Filter on Status / Owner / Priority to route work. Concern & Disagreement (red) need attention first. | [7 empty] | Colours are to focus attention on most important items that need discussion
ID | Area | Section | Requirement | Priority | Proposed Priority | Classification | Design response | Arch/Engineering response | Status | Owner | Technical Comment | Flag / Recommended Action | overall RAG
TA-01 | Technical Architecture | Core Architecture | High-level architectural diagrams MUST exist and be accessible for peer review. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-02 | Technical Architecture | Core Architecture | The architectural style (e.g. Cloud, SaaS, N-Tier, µ-services) MUST be clearly defined and documented with supporting diagrams (activity, sequence, data flow, deployment). | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-03 | Technical Architecture | Core Architecture | Data flow MUST be documented, including how data is ingested, validated and screened from third parties. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-04 | Technical Architecture | Core Architecture | The solution MUST follow a standard µ-service or enterprise application architecture pattern. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Do not mandate microservices. Require an architecture pattern appropriate to the product context.
TA-05 | Technical Architecture | Core Architecture | Service implementations MUST be governed at the correct functional granularity to support independent scalability. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Independent scalability is only required where components have distinct scaling needs; functional boundaries should drive decomposition.
TA-06 | Technical Architecture | Core Architecture | The degree of coupling between services and components MUST be assessed and minimised; abstractions MUST be in place to manage complexity. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-07 | Technical Architecture | Core Architecture | Open source usage MUST be documented; code-back obligations MUST be identified and the relevant code MUST be segregated (e.g. separate repo with binary dependency consumption). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-08 | Technical Architecture | Core Architecture | Interconnectivity standards MUST be defined and implemented (e.g. RESTful/resource-based URLs, GraphQL, JSON, XML, AVRO). | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-09 | Technical Architecture | Core Architecture | System orchestration MUST support pre-emptive and time-based scaling. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Pre-emptive/time-based scaling is context-dependent. Autoscaling strategy should be based on actual workload characteristics.
TA-10 | Technical Architecture | Core Architecture | Memory consumption MUST be controlled; each instance MUST be independent from a memory standpoint relative to input data. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Control memory usage, but the wording about instance independence should be interpreted according to the runtime and state model.
TA-11 | Technical Architecture | Core Architecture | Major components MUST be compartmentalised, with assigned guardians/gatekeepers responsible for conceptual integrity. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Component ownership is useful, but named guardians/gatekeepers are an operating-model choice rather than a universal architecture requirement.
TA-12 | Technical Architecture | Core Architecture | Code MUST be traceable to architectural designs; architectural documentation MUST be maintained as living documents. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-13 | Technical Architecture | Core Architecture | Where the system is defined as a platform, a platform API MUST be formally defined and enforced. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-14 | Technical Architecture | Core Architecture | The data layer MUST be abstracted sufficiently to permit independent migration (e.g. RDBMS to NoSQL) without requiring changes to business logic. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Database portability should not be mandated. Decouple persistence from business logic where useful, but avoid designing for hypothetical RDBMS-to-NoSQL migration.
TA-15 | Technical Architecture | Core Architecture | Architecture MUST support testability, for example through Dependency Injection. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-16 | Technical Architecture | Core Architecture | Architecture MUST support forward compatibility and extensibility. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-17 | Technical Architecture | Core Architecture | Sensitive data (passwords, access keys) stored in variables MUST be ephemeral; actuator endpoints MUST be access-controlled. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-18 | Technical Architecture | Core Architecture | If the system is part of a product family/program line, common functionality MUST be abstracted, the shared layer MUST be clearly defined, and compatibility MUST be enforced. | SHOULD | SHOULD | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-19 | Technical Architecture | Availability, Resiliency and Fault Tolerance | Resiliency MUST be designed into the architecture (e.g. caching, redundancy, immediate data persistence, replication, binary versioning, backward compatibility, Helm-managed rollout/rollback). | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-20 | Technical Architecture | Availability, Resiliency and Fault Tolerance | A minimum set of functionality MUST remain available if a major component (e.g. the database) is unavailable. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Graceful degradation should be defined for critical dependencies, but the application cannot always remain useful when a primary datastore is unavailable.
TA-21 | Technical Architecture | Availability, Resiliency and Fault Tolerance | The system MUST support retry logic for transient failures before surfacing errors to the end user. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-22 | Technical Architecture | Availability, Resiliency and Fault Tolerance | Idempotent operations MUST be identified and documented; such operations MUST be safely retryable. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-23 | Technical Architecture | Availability, Resiliency and Fault Tolerance | Redundancy and failover plans MUST exist, including defined data synchronisation frequency across zones. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-24 | Technical Architecture | Availability, Resiliency and Fault Tolerance | A disaster recovery plan and a backup plan MUST exist, including backup frequency and retention period. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-25 | Technical Architecture | Availability, Resiliency and Fault Tolerance | The system MUST support circuit breaker functionality to prevent cascading failures (e.g. Hystrix, Steeltoe for .NET). | MUST | SHOULD | Questionable Requirement |  |  |  |  | Use circuit breakers only for suitable remote/dependency calls; the pattern is not mandatory for every component.
TA-26 | Technical Architecture | Availability, Resiliency and Fault Tolerance | APIs MUST be designed to tolerate extraneous or unexpected data input. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-27 | Technical Architecture | Availability, Resiliency and Fault Tolerance | Errors and faults MUST be clearly reported to users and aggregated/communicated back to data sources. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-28 | Technical Architecture | Availability, Resiliency and Fault Tolerance | The system SHOULD implement an event sourcing model for application state. | SHOULD | COULD | Questionable Requirement |  |  |  |  | Event sourcing is an architectural pattern, not a default requirement. Use only when audit/history and state-transition needs justify the complexity.
TA-29 | Technical Architecture | Availability, Resiliency and Fault Tolerance | The system SHOULD support non-essential functionality being disabled under high load (equivalent to dark launch) to preserve responsiveness. | SHOULD | COULD | Questionable Requirement |  |  |  |  | Load shedding/degraded-mode capability is valuable only where workload and availability objectives justify it.
TA-30 | Technical Architecture | Performance and Scalability | Optimisation strategies MUST be defined, with documented maximum concurrent user capacity and maximum tolerable load. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-31 | Technical Architecture | Performance and Scalability | The system MUST be horizontally or vertically scalable; a pre-emptive orchestration process MUST be in place. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Scalability is required, but pre-emptive orchestration should not be mandatory; reactive or scheduled scaling may be sufficient.
TA-32 | Technical Architecture | Performance and Scalability | Critical paths and most resource-intensive components MUST be identified. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-33 | Technical Architecture | Performance and Scalability | µ-services MUST be defined at the correct functional granularity to enable independent scalability. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Only applicable if the target architecture uses microservices. Service boundaries should be driven by domain and scaling needs.
TA-34 | Technical Architecture | Performance and Scalability | µ-service guidelines/principles MUST be in place to enforce scalable characteristics of each service. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Only applicable if the target architecture uses microservices; otherwise replace with general service/component design principles.
TA-35 | Technical Architecture | Performance and Scalability | A performance review process MUST exist, including a defined testing policy, tooling (e.g. JMeter) and frequency. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-36 | Technical Architecture | Performance and Scalability | A caching system MUST be in place (e.g. Memcache, Redis). | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Caching must not be mandated by default. Introduce caching only where performance analysis identifies a need.
TA-37 | Technical Architecture | Performance and Scalability | Intra µ-service traffic MUST be managed with routing, policy enforcement and security (e.g. Istio). | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | A service mesh such as Istio is not a default requirement. Apply routing/policy/security controls appropriate to the chosen deployment model.
TA-38 | Technical Architecture | Performance and Scalability | Flow control mechanisms (e.g. Kafka at data ingestion) SHOULD be in place to handle demand spikes. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Kafka or another flow-control mechanism is only needed for asynchronous/high-volume ingestion scenarios.
TA-39 | Technical Architecture | Information and Data Architecture | Data replication, persistence and sharding MUST be handled and guaranteed; sharding strategy MUST be documented. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Persistence and integrity matter, but replication/sharding are context-dependent and should not be mandatory if the data scale does not require them.
TA-40 | Technical Architecture | Information and Data Architecture | A schema update and versioning process MUST be established; data format evolution (e.g. AVRO schema evolution) MUST be documented. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-41 | Technical Architecture | Information and Data Architecture | GDPR compliance MUST be in place, including edge cases such as restoring from backup after a GDPR deletion action. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
TA-42 | Technical Architecture | Information and Data Architecture | Data integrity MUST be enforced (e.g. file checksums). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-43 | Technical Architecture | Information and Data Architecture | Security scanning MUST be performed on all data input (virus scanning, active content filtering). | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Malware/active-content scanning is relevant for file/content ingestion, not necessarily for every input field or API payload.
TA-44 | Technical Architecture | Information and Data Architecture | The system MUST be protected against SQL injection (parameterised/prepared statements; no dynamic query concatenation). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-45 | Technical Architecture | Information and Data Architecture | Data validation MUST be comprehensive, covering type, size, semantic and coherency checks. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-46 | Technical Architecture | Information and Data Architecture | Financial transactions MUST use appropriate data types. | MUST | N/A / CONDITIONAL | Not Applicable / Conditional |  |  |  |  | Only applicable if the product performs financial calculations or transactions.
TA-47 | Technical Architecture | Information and Data Architecture | Jurisdictional limitations on data storage MUST be identified and complied with. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
TA-48 | Technical Architecture | Information and Data Architecture | The backup and disaster recovery process for data MUST be defined and documented. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-49 | Technical Architecture | Information and Data Architecture | Eventual consistency trade-offs SHOULD be evaluated and documented for each applicable use case. | SHOULD | SHOULD | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-50 | Technical Architecture | Integrations and Extensibility | All third-party system integrations MUST be documented. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-51 | Technical Architecture | Integrations and Extensibility | A platform API MUST be provided and documented; versioning cadence MUST be defined. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Only applicable if AIPR is intended to expose a platform API. Internal APIs can still require documentation/versioning without defining a product platform API.
TA-52 | Technical Architecture | Integrations and Extensibility | API, SPI and plug-in points MUST be well documented and kept up to date. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | SPI/plugin documentation is only applicable if extension/plugin points exist.
TA-53 | Technical Architecture | Integrations and Extensibility | Compliance with the defined API MUST be enforced. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
TA-54 | Technical Architecture | Integrations and Extensibility | Data formats and interaction methods MUST support extensibility; schemas MUST support data extension without breaking changes. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
TA-55 | Technical Architecture | Integrations and Extensibility | Industry standards supported by the system MUST be documented, including their configuration, customisation and extension capabilities. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Document only the external/industry standards actually applicable to the product.
TA-56 | Technical Architecture | Deployment and Infrastructure | The deployment process MUST be automated; manual steps MUST be minimised and documented. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-57 | Technical Architecture | Deployment and Infrastructure | A rollback process MUST be in place (e.g. Helm chart–managed rollback). | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-58 | Technical Architecture | Deployment and Infrastructure | Zero or minimal downtime deployment MUST be targeted. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-59 | Technical Architecture | Deployment and Infrastructure | A feature enablement process MUST be in place (e.g. dark launch), with decisions recorded, and segmentation options available at user, organisation or global level. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Feature flags are useful, but user/organisation/global segmentation should be required only where product rollout needs it.
TA-60 | Technical Architecture | Deployment and Infrastructure | Multiple deployment scenarios (on-premise, cloud, hybrid) MUST be supported with consistent tooling and scripts. | MUST | N/A / CONDITIONAL | Not Applicable / Conditional |  |  |  |  | Supporting on-prem, cloud and hybrid deployment is a product-scope decision, not a universal technical requirement.
TA-61 | Technical Architecture | Deployment and Infrastructure | All cloud accounts MUST be enrolled under or have TSG as the parent organisation. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
TA-62 | Technical Architecture | Deployment and Infrastructure | The security pillar of the applicable cloud Well-Architected Framework (AWS or Azure) MUST be rigorously applied. | SHOULD | SHOULD | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
TA-63 | Technical Architecture | Regulatory and Compliance | The system MUST support all applicable regulatory compliance standards (e.g. Sarbanes-Oxley, GDPR). | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
TA-64 | Technical Architecture | Regulatory and Compliance | Contractual data requirements (e.g. data residency, filtering by user location) MUST be enforced by the system. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
TA-65 | Technical Architecture | Regulatory and Compliance | The product MUST comply with Bain's Building Tools Hosting Sensitive Information Policy, Data Classification Policy, Client Privacy Policy, Key Management and Cryptography Policy, and Secure SDLC Policy. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
AD-01 | Application Design | Accessibility and User Experience | The solution MUST support accessibility, including screen reader compatibility, reduced vision support and partial colour-blindness accommodation. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
AD-02 | Application Design | Accessibility and User Experience | Where colour is used to communicate information, it MUST be augmented by additional cues (e.g. shapes, labels). | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
AD-03 | Application Design | Accessibility and User Experience | The UI MUST be responsive across desktop, tablet and mobile viewports. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
AD-04 | Application Design | Accessibility and User Experience | The solution MUST have clearly defined actors, use cases, scenarios, workflows and storyboards. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
AD-05 | Application Design | Accessibility and User Experience | A process MUST exist to gather, aggregate, filter and prioritise user feedback. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
AD-06 | Application Design | Accessibility and User Experience | User Centred Design MUST be integrated with the development process; usability issues MUST be documented and communicated to stakeholders. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
AD-07 | Application Design | Accessibility and User Experience | Accessibility compliance MUST be tested regularly; the frequency and method of testing MUST be documented. | SHOULD | SHOULD | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
AD-08 | Application Design | Accessibility and User Experience | Affordances of new widgets and interfaces MUST be analysed (cognitive, physical, sensory, functional) before release. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
AD-09 | Application Design | Configuration and Customisation | The system MUST support SSO through integration with a third-party Identity Provider (e.g. Azure AD, Okta), in addition to local authentication. | MUST | MUST (SSO) / CONDITIONAL (local auth) | Questionable Requirement |  |  |  |  | SSO is appropriate for enterprise access. Requiring local authentication in addition to SSO can increase security and support burden and should not be mandatory unless there is a defined need.
AD-10 | Application Design | Configuration and Customisation | The system MUST support granular, role-based authorisation including native roles, custom roles and, where required, per-field level access control. | MUST | MUST (RBAC) / CONDITIONAL (custom & field-level) | Questionable Requirement |  |  |  |  | RBAC is important, but custom roles and field-level permissions should be driven by product requirements rather than mandated by default.
AD-11 | Application Design | Configuration and Customisation | The system SHOULD support customisation of forms, fields, workflows, business processes and reporting. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Forms/workflow/report customisation is a product feature, not a general architecture requirement.
AD-12 | Application Design | Configuration and Customisation | A template approach for reuse and rapid deployment SHOULD be in place, with a defined template creation process. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Template support is a product capability and should be driven by use cases.
AD-13 | Application Design | Mobility and Internationalisation | If mobile access is required, the system MUST support it; known limitations on mobile MUST be documented. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Conditional on mobile access being in scope.
AD-14 | Application Design | Mobility and Internationalisation | User-facing strings and API responses MUST be abstracted and parameterised to support localisation. | MUST | SHOULD / CONDITIONAL | Questionable Requirement |  |  |  |  | Localisation abstraction is useful only if localisation/multi-language support is in scope or expected.
AD-15 | Application Design | Mobility and Internationalisation | The UI MUST support bi-directional text (bidi) if double-byte language environments are required. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Conditional on RTL/bidi language support being in scope; “double-byte” and bidi are separate concerns.
AD-16 | Application Design | Mobility and Internationalisation | Interfaces and charts MUST be fully responsive on tablet and phone views. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Responsive tablet/phone support should match the agreed supported-device scope.
AD-17 | Application Design | Mobility and Internationalisation | Supported browsers and versions MUST be documented. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
AD-18 | Application Design | Mobility and Internationalisation | Native iOS and Android apps SHOULD be available or on the product roadmap if mobile access is required. | SHOULD | COULD / CONDITIONAL | Questionable Requirement |  |  |  |  | Native mobile apps are not required merely because mobile browser access is needed.
AD-19 | Application Design | Access Control | The system MUST NOT permit anonymous access. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
AD-20 | Application Design | Access Control | RBAC with defined separation of duties MUST be in place; each role MUST be assessed against the principle of least privilege. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
AD-21 | Application Design | Access Control | SSO and MFA MUST be set up for all user accounts. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
AD-22 | Application Design | Access Control | Unit and integration tests MUST cover ACL and access control scenarios. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
AD-23 | Application Design | Access Control | Organisation-level admin configuration SHOULD be available for access control delegation. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Delegated organisation-level administration is a product/tenancy requirement, not a default access-control requirement.
AD-24 | Application Design | Reporting and Observability | The system MUST support distributed tracing, log aggregation, audit logging and health checking. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
AD-25 | Application Design | Reporting and Observability | Log scrubbing and cleansing for sensitive data MUST be implemented. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
AD-26 | Application Design | Reporting and Observability | Customisable reports and dashboards SHOULD be available to users. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | User-facing custom reports/dashboards are product features and should be required only if supported by use cases.
AD-27 | Application Design | Reporting and Observability | Native BI tool connectors (e.g. Tableau, Power BI) SHOULD be available. | SHOULD | COULD / CONDITIONAL | Questionable Requirement |  |  |  |  | Native BI connectors are integration/product features and should be justified by reporting requirements.
AD-28 | Application Design | Reporting and Observability | The system SHOULD support embedding third-party reports via iframes or SDKs. | COULD | COULD / CONDITIONAL | Questionable Requirement |  |  |  |  | Embedding third-party reports is optional and should be driven by reporting architecture.
CQ-01 | Code Quality | Pipeline and Quality Gates | Quality metrics MUST be enforced via the CI/CD pipeline, including code coverage thresholds, code smell checks and code style enforcement (e.g. SonarQube). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-02 | Code Quality | Pipeline and Quality Gates | Security checks MUST be enforced by the pipeline; high and critical severity defects MUST block delivery. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-03 | Code Quality | Pipeline and Quality Gates | License and dependency scanning MUST be enforced by the pipeline (e.g. npm audit, Snyk). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-04 | Code Quality | Pipeline and Quality Gates | Static analysis checks MUST be enforced via the pipeline. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-05 | Code Quality | Pipeline and Quality Gates | Unit and integration tests MUST run on every pull request. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-06 | Code Quality | Pipeline and Quality Gates | OWASP ZAP dynamic scanning MUST run on every pull request (as a GitHub Action). | MUST | SHOULD | Questionable Requirement |  |  |  |  | DAST is valuable, but requiring OWASP ZAP on every pull request is tool- and cadence-specific. Define risk-based DAST in the pipeline instead.
CQ-07 | Code Quality | Pipeline and Quality Gates | Snyk or Wiz MUST run continuously (Bain is currently transitioning from Snyk to Wiz); SonarQube and CodeQL SHOULD run continuously. | MUST / COULD | MUST (capability) / TOOL TBD | Questionable Requirement |  |  |  |  | Security scanning is required, but specific vendor tools and continuous cadence should follow Bain platform standards and environment constraints.
CQ-08 | Code Quality | Pipeline and Quality Gates | GitHub Secret Scanning MUST be enabled and continuously active. | MUST | MUST (capability) / PLATFORM TBD | Questionable Requirement |  |  |  |  | Secret scanning should be mandatory, but GitHub-specific implementation applies only if GitHub is the source-control platform.
CQ-09 | Code Quality | Pipeline and Quality Gates | A clear and definitive promotion process MUST be in place covering all environments (dev, QA, staging, production). | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
CQ-10 | Code Quality | Pipeline and Quality Gates | Artefact versioning MUST be supported (e.g. JFrog Artifactory). | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
CQ-11 | Code Quality | Repository and Code Standards | The main/master branch MUST be the definitive source of truth; branches MUST only be used for short-lived feature development. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Protect the main branch and define a branching strategy; short-lived branches are a preferred practice, not universally mandatory.
CQ-12 | Code Quality | Repository and Code Standards | Each component/µ-service MUST reside in its own repository. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Repository-per-service is a source-control strategy, not a universal requirement. Monorepo and multi-repo models can both be valid.
CQ-13 | Code Quality | Repository and Code Standards | Each repository MUST have a clear README documenting dependencies, input/output form and a reference to API documentation. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-14 | Code Quality | Repository and Code Standards | API documentation MUST be co-located with code (e.g. Swagger/OpenAPI). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-15 | Code Quality | Repository and Code Standards | Code MUST be traceable to the underlying story, epic, requirements document and UX designs via the SCM system. | MUST | SHOULD | Questionable Requirement |  |  |  |  | Traceability is valuable, but exact linkage from every code change to every artefact should be proportional to governance needs.
CQ-16 | Code Quality | Repository and Code Standards | A standard code structure MUST be in place for each component/µ-service. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-17 | Code Quality | Repository and Code Standards | Adopted style guides and coding conventions MUST be documented and enforced. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-18 | Code Quality | Repository and Code Standards | A code review checklist MUST be in place; a developer manifesto SHOULD be documented. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-19 | Code Quality | Repository and Code Standards | Access to individual repositories SHOULD be restricted to the developers/teams assigned to those components. | SHOULD | SHOULD | Questionable Requirement |  |  |  |  | Least-privilege repository access is appropriate, but strict team-only repo isolation may hinder collaboration and is an organisational policy choice.
CQ-20 | Code Quality | Repository and Code Standards | A defined API design process MUST be in place, adhering to specific standards (e.g. Google resource-based URLs, RESTful, GraphQL). | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
CQ-21 | Code Quality | Secure Coding | Parameterised and prepared statements MUST be used for all SQL; dynamic query construction via string concatenation is prohibited. | MUST | CONDITIONAL | Questionable Requirement |  |  |  |  | Applicable only if SQL-based persistence is used.
CQ-22 | Code Quality | Secure Coding | Input validation (active content filtering), output encoding, error handling and logging MUST follow good security programming practice. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-23 | Code Quality | Secure Coding | HTTPS MUST be enforced on all inter-service communication. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-24 | Code Quality | Secure Coding | Sufficient API security controls MUST be in place: throttling, credential security, input validation, access control and replay vulnerability protection. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-25 | Code Quality | Secure Coding | No internal, structural or technical information MUST be leaked via API responses; all exceptions MUST be logged with appropriate HTTP status codes. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-26 | Code Quality | Secure Coding | A Content Security Policy MUST be implemented. | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Applicable to browser-based web applications; exact CSP policy depends on frontend architecture and embedded-content needs.
CQ-27 | Code Quality | Secure Coding | HTTP body size limits MUST be set per content-type middleware. | SHOULD | SHOULD | Questionable Requirement |  |  |  |  | Request/body size limits should be risk-based and endpoint/content-type specific, not a blanket arbitrary limit.
CQ-28 | Code Quality | Secure Coding | No deprecated packages or framework versions MUST be in use. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
CQ-29 | Code Quality | Secure Coding | Applications MUST NOT run with root privileges. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-30 | Code Quality | Secure Coding | Regex expressions MUST be protected against ReDoS attacks (e.g. using safe-regex). | SHOULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Applicable where complex/user-influenced regular expressions are used; use runtime timeouts or safe patterns as appropriate.
CQ-31 | Code Quality | Secure Coding | Redirect/forward parameters MUST NOT be used to reify destinations without protective constraints. | COULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Applicable only where redirect/forward parameters exist.
CQ-32 | Code Quality | Secure Coding | All functionality disabled via UI controls MUST also be disabled via API access. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-33 | Code Quality | Secure Coding | Upload functionality MUST be segregated from core application logic to prevent zip bomb attacks. | COULD | CONDITIONAL | Questionable Requirement |  |  |  |  | Applicable only if file/archive upload is supported. Controls should address zip bombs and content scanning without mandating a particular component split.
CQ-34 | Code Quality | Secure Coding | System passwords and access tokens MUST be stored securely and injected via pipeline secrets (AWS Secrets Manager / Azure Key Vault / Kubernetes Secrets); no credentials hardcoded. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
CQ-35 | Code Quality | Maintainability and Evolvability | The system MUST be designed to facilitate change; decisions likely to change MUST be consistently abstracted. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
CQ-36 | Code Quality | Maintainability and Evolvability | Interfaces between major components MUST be formally defined. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
CQ-37 | Code Quality | Maintainability and Evolvability | Coupling between major components MUST be loose; DAO layer complexity MUST be controlled (minimal stored procedures, managed join depth). | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
CQ-38 | Code Quality | Maintainability and Evolvability | The architecture SHOULD be technology-agnostic; tools to mitigate vendor lock-in SHOULD be used (e.g. MyBatis for DB abstraction). | SHOULD | SHOULD | Questionable Requirement |  |  |  |  | Avoid unnecessary lock-in where it provides business value, but technology agnosticism should not override use of managed cloud capabilities. MyBatis is not a general solution.
CQ-39 | Code Quality | Maintainability and Evolvability | The data format in the service layer SHOULD be decoupled from the data format in the DB layer. | SHOULD | SHOULD | Questionable Requirement |  |  |  |  | Avoid leaking persistence models into service contracts, but separate DTO/domain models should be used where they add value rather than by mandate.
CQ-40 | Code Quality | Maintainability and Evolvability | The current technology stack and versions in use MUST be documented. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
SD-01 | Software Dev Principles | Security Culture and Practice | The team MUST adhere to a standardised set of security best practices (OWASP guidelines). | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-02 | Software Dev Principles | Security Culture and Practice | The team MUST periodically review the OWASP Top 10 and relevant security educational resources. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-03 | Software Dev Principles | Security Culture and Practice | Security training MUST be part of the on-boarding process for all new engineering employees. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-04 | Software Dev Principles | Security Culture and Practice | A threat modelling exercise MUST be conducted for the product. | SHOULD | SHOULD | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
SD-05 | Software Dev Principles | Security Culture and Practice | A full security risk assessment and a security architecture review with TSG Security MUST be conducted. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-06 | Software Dev Principles | Security Culture and Practice | Independent penetration testing MUST be conducted periodically (minimum annually via Rapid 7). | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-07 | Software Dev Principles | Security Culture and Practice | A dedicated security champion SHOULD be assigned to the team and to security-related alerts in tooling. | COULD | COULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-08 | Software Dev Principles | Security Culture and Practice | A secure review checklist SHOULD be in place as part of the development process. | COULD | COULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-09 | Software Dev Principles | Security Culture and Practice | The team MUST be familiar with the TSG API Security Guidance and the TSG Secure Design Principles. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-10 | Software Dev Principles | Security Culture and Practice | The system MUST be designed with reference to the TSG Secure Design Principles; security MUST NOT rely on obscurity. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-11 | Software Dev Principles | Security Culture and Practice | The CI/CD pipeline MUST be configured to automatically block delivery for high or critical severity defects. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-12 | Software Dev Principles | Data and Privacy Principles | Data MUST be encrypted at rest and in flight. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-13 | Software Dev Principles | Data and Privacy Principles | No data MUST be stored on personal developer machines. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-14 | Software Dev Principles | Data and Privacy Principles | No client data MUST be stored in repositories with shared access. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-15 | Software Dev Principles | Data and Privacy Principles | Client data used for testing or development MUST have explicit client consent, a contractual agreement and sufficient anonymisation. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-16 | Software Dev Principles | Data and Privacy Principles | A defined and approved process MUST be in place for client-to-client data segregation. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
SD-17 | Software Dev Principles | Data and Privacy Principles | GDPR protections MUST be applied: pseudo-anonymisation, data residency compliance, Subject Access Request compliance, and minimum necessary data usage. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-18 | Software Dev Principles | Data and Privacy Principles | The Bain Data Classification Standards MUST be applied to all data handled by the product. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-19 | Software Dev Principles | Data and Privacy Principles | When sending data to third-party services, logs and API calls MUST be scrubbed for PII; any exception requires TSG Security approval. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-20 | Software Dev Principles | Data and Privacy Principles | No third-party service MUST have direct database or blob storage access without TSG Security approval. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-21 | Software Dev Principles | Data and Privacy Principles | Production and non-production datasets MUST be strictly segregated. | SHOULD | SHOULD | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
SD-22 | Software Dev Principles | Data and Privacy Principles | Publicly exposed artefacts (URLs, configurations, filenames, error codes, HTTP responses) MUST be periodically verified to contain no client names or confidential information. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
SD-23 | Software Dev Principles | Developer Access and Credential Management | RBAC with defined separation of duties MUST be in place across all systems. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-24 | Software Dev Principles | Developer Access and Credential Management | Developers MUST NOT use shared credentials to access resources. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-25 | Software Dev Principles | Developer Access and Credential Management | MFA MUST be required for individual access to all production systems. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-26 | Software Dev Principles | Developer Access and Credential Management | All service accounts MUST comply with TSG standards. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-27 | Software Dev Principles | Developer Access and Credential Management | Developer access to production machines and sensitive client information MUST be limited and controlled. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-28 | Software Dev Principles | Developer Access and Credential Management | Passwords and credentials MUST be rotated regularly (e.g. every 3 months). | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-29 | Software Dev Principles | Developer Access and Credential Management | Full disk encryption MUST be enforced across development machines; OS and tool updates MUST be enforced. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-30 | Software Dev Principles | Developer Access and Credential Management | No product application MUST run with root privileges. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-31 | Software Dev Principles | Team Organisation and Knowledge Management | Teams SHOULD be aligned with major system components; integration points between teams MUST be formally specified. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-32 | Software Dev Principles | Team Organisation and Knowledge Management | Cross-cutting concerns MUST be enforced between teams (e.g. via chapter leads). | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-33 | Software Dev Principles | Team Organisation and Knowledge Management | Knowledge MUST be captured in wikis, documentation, diagrams, videos and tutorials; knowledge retention MUST be actively facilitated. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-34 | Software Dev Principles | Team Organisation and Knowledge Management | Critical actors/single points of failure MUST be identified and mitigated through cross-training and documentation. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-35 | Software Dev Principles | Team Organisation and Knowledge Management | Best practices and top-performer workflows MUST be captured and disseminated across the organisation. | SHOULD | SHOULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-36 | Software Dev Principles | Team Organisation and Knowledge Management | A process MUST be in place to avoid single points of failure in team knowledge and component ownership. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-37 | Software Dev Principles | Team Organisation and Knowledge Management | All tools and technologies used MUST be approved; a Technology Risk Assessment (TRA) MUST be in place for each. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-38 | Software Dev Principles | Team Organisation and Knowledge Management | A Vendor Risk Assessment MUST be in place for all third-party vendors, initiated at the beginning of first engagement. | MUST | MUST | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.
SD-39 | Software Dev Principles | Development Process | A structured software development process MUST be followed (e.g. Agile). | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-40 | Software Dev Principles | Development Process | Developers MUST have the ability to work independently against a representative local instantiation of the system. | MUST | SHOULD | Questionable Requirement |  |  |  |  | A fully representative local instantiation may be impractical for cloud-native/external-service-heavy systems. Developers need an effective local/test workflow, not necessarily the full system locally.
SD-41 | Software Dev Principles | Development Process | A defined bug identification, reporting, triage and prioritisation process MUST be in place. | MUST | MUST | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-42 | Software Dev Principles | Development Process | Hot-fixes MUST be issued for critical bugs; high and critical security defects MUST be addressed in the sprint following discovery. | MUST | MUST (risk-based SLA) | Questionable Requirement |  |  |  |  | Critical security issues need defined SLAs; “the following sprint” may be too slow or too rigid depending on severity.
SD-43 | Software Dev Principles | Development Process | Architectural transformations MUST be documented with an assessment of risks and mitigation steps before execution. | MUST | MUST | Applicable – D&D |  |  |  |  | Valid architecture/design concern. Define the target approach and decision during D&D; implementation evidence can follow during delivery.
SD-44 | Software Dev Principles | Development Process | Technical debt from prior architectural transformations MUST be tracked and addressed. | SHOULD | SHOULD | Applicable – Development |  |  |  |  | Valid implementation/engineering requirement. The architecture should enable it, but concrete evidence is expected during development and CI/CD rather than as a complete D&D deliverable.
SD-45 | Software Dev Principles | Development Process | A backup strategy MUST be defined, including backup frequency, retention period and restoration process. | MUST | MUST | Applicable – Operations |  |  |  |  | Valid requirement, but evidence is expected mainly through deployment/production readiness, operational procedures or runbooks rather than Design & Define alone.
SD-46 | Software Dev Principles | Development Process | Backups MUST be encrypted and access restricted to designated DevOps/Solutions Architects; restoration MUST NOT reintroduce outdated library or software versions. | MUST | MUST (backup security only) | Questionable Requirement |  |  |  |  | Encryption/access control for backups is valid; preventing restoration of old library versions is not normally a backup responsibility and should be handled by deployment/patch management.
SD-47 | Software Dev Principles | Development Process | An incident response plan MUST be defined and periodically exercised, aligned with the TSG Cyber Incident Management Policy. | COULD | COULD | External Dependency |  |  |  |  | Applicable, but confirmation/ownership sits partly outside the delivery team (e.g. Bain/TSG Security, Infra, Governance or organisational policy). Capture the dependency rather than treating the delivery team as sole owner.

## Summary
ARC v2 Architecture Assessment Tracker
Sheet "Summary"
Last changed on: 29-Jul-2026 |  |  |  | / DRAFT
Summary
Status \ Area | Technical Architecture | Application Design | Code Quality | Software Dev Principles | Total
Addressed | 0 | 0 | 0 | 0 | 0
Planned | 0 | 0 | 0 | 0 | 0
Open decision | 0 | 0 | 0 | 0 | 0
Needs security/infra review | 0 | 0 | 0 | 0 | 0
Gap | 0 | 0 | 0 | 0 | 0
Concern | 0 | 0 | 0 | 0 | 0
Disagreement | 0 | 0 | 0 | 0 | 0
N/A - confirm scope | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0
Owner | Count
Echelon Eng | 0
Ridwan & Corey | 0
Bain / Joy | 0
Design | 0
Architecture Review / Governance | 0
Total | 0
Key figures
Total requirements | 180
Addressed | 0
MUST requirements | 136
MUST not yet Addressed / not N-A | 136
Concerns + Disagreements | 0
Gaps | 0
Items routed to Ridwan & Corey | 0

## Action Items
ARC v2 Architecture Assessment Tracker
Sheet "Action Items"
Last changed on: 29-Jul-2026 |  |  |  | / DRAFT
Action Items — Concerns & Disagreements
Items flagged red on the Tracker. Sorted: Concerns then Disagreements.
ID | Priority | Status | Requirement | Issue / Recommended action | Owner
AD-01 | MUST | Concern
AD-02 | MUST | Disagreement