## Discovery Workplan
OI 3.0 · Discovery Phase Workplan (Phase 0, Weeks 1–4)
Prepared by Bain ¦ For StatusNeo ¦ 6 FTE · 4 weeks · 20 working days ¦ Exit gate: Discovery sign-off + CoE gate ¦ Workshops: TBD ¦ 💡 To shift all dates, change cell F5
| Track | Deliverable / Activity | Owner (SN unless stated) | Output / Artefact | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Notes / Bain dependency | Status
[5 empty] | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25
BAIN INPUTS — gating milestones, Bain-owned
| Bain Input | ✓ UX designer assigned and available | Bain Design | Designer on-boarded | [20 empty] | ✓ Joanna on-boarded — complete | bar: 2026-07-29 to 2026-07-30
| Bain Input | Calculation (VCC) schema workshop scheduled | Bain VCC | Workshop held; schema draft agreed | [20 empty] | Required by end Week 1; unblocks contract-first build | bar: 2026-07-31 to 2026-08-03
| Bain Input | Glean / Iris / ARC access granted | Bain KM | Sandbox access confirmed | [20 empty] | Needed for retrieval eval harness in Week 3 | bar: 2026-07-31 to 2026-08-03
| Bain Input | VRA intake engaged | Bain Security | VRA scoping underway | [20 empty] | Keeps security review parallel, not back-loaded | bar: 2026-07-31 to 2026-08-03
| Bain Input | Coding-agent plan + token budget confirmed | Bain IT | AI model access + Copilot confirmed | [20 empty] | Required before dev environment setup | bar: 2026-07-31 to 2026-08-03
| Bain Input | Data-source access granted | Bain | Access log confirmed per source | [20 empty] | Owners: VCC/Jason Barnes, KM, PEG, FRWD teams | bar: 2026-08-12 to 2026-08-13
TRACK 1 · BUSINESS AND PRODUCT Engagement Lead, AI-Native Functional Consultant | bar: 2026-08-24 to 2026-08-25
| Track 1 | Kickoff meeting — team introductions, contacts, ways of working, communication channels | Kasia | Agreed comms channels; contacts list; ways of working doc | [20 empty] | Day 1 — before any other activity begins | bar: 2026-07-29
| Track 1 | Confirm Iris/ARC metadata structure and sample canonical questions | Bain KM (TBC) | Metadata structure doc; list of canonical questions for retrieval eval | [20 empty] | Feeds retrieval eval harness in Track 4 — needed early | bar: 2026-07-29 to 2026-08-03
| Track 1 | Current-state walkthrough of OI 2.0 — process, data sources, outputs, and Partner pain points | Bain BCN | As-is process doc; SN sign-off that current state is understood | [20 empty] | Bain BCN to run session with SN in Week 1 — foundational input before any design work begins | bar: 2026-07-29 to 2026-08-03
| Track 1 | Align business objectives and KPIs | EL + FC | Agreed objectives and KPI doc | bar: 2026-07-29 to 2026-08-06
| Track 1 | User journeys and stories | FC | User journey maps; story cards (in progress) | [20 empty] | Building on Joanna's prototype — continuing | bar: 2026-07-29 to 2026-08-12
| Track 1 | PRE-WORKSHOP: Consolidate BRD draft | FC + EL | Draft BRD for Workshop 1 review | [20 empty] | Input to Business Kick-off Workshop 4–6 Aug | bar: 2026-08-05 to 2026-08-13
| Track 1 | PRE-WORKSHOP: Prepare MVP scope options for business sign-off | EL | MVP scope options doc; decision paper | [20 empty] | Bain PM to review before Workshop 1 | bar: 2026-08-12 to 2026-08-17
| Track 1 | PRE-WORKSHOP: Define business KPIs and success criteria (draft) | FC + EL | Draft KPI list for workshop validation | [20 empty] | To be finalised and agreed at Workshop 1 | bar: 2026-08-05 to 2026-08-13
| Track 1 | MVP backlog + Industrialisation split | FC + EL | Prioritised Jira backlog with story points | [20 empty] | Bain PM sign-off required; feeds Workshop 2.1 | bar: 2026-08-12 to 2026-08-20
| Track 1 | Pilot cohort + success metrics | EL | Pilot plan; success criteria doc | bar: 2026-08-12 to 2026-08-20
| Track 1 | Finalise scoped roadmap (MVP vs. Industrialisation) | EL | Signed roadmap; delivery recommendation | [20 empty] | Bain Steering Committee sign-off | bar: 2026-08-19 to 2026-08-25
| Workshop | WORKSHOP 1: Business Kick-off (2–3 days, TBD) | Bain LT + SN LT | Agreed: objectives, KPIs, MVP scope, governance, risks, measures of success | [20 empty] | On-site: Noah, Kasia, Sandeep, Siva ¦ Remote: Michelle, Dean | bar: 2026-08-07 to 2026-08-11
TRACK 2 · ARCHITECTURE AND DATA AI Agent Architect, Lead Full Stack Engineer
| Track 2 | VCC integration discovery session — confirm MCP capability for programmatic agent calls, runtime vs. batch, and schema | Joint — SN Architect + Jason Barnes (VCC) + Sandeep | VCC integration contract / findings doc; schema agreed or escalated | [20 empty] | ⚠ Biggest unresolved architecture risk — MCP-only constraint not yet confirmed for agent use; must not be treated as resolved until this session | bar: 2026-07-29 to 2026-08-03
| Track 2 | PRE-WORKSHOP: Document current-state architecture assumptions | Architect | Current-state architecture summary | [20 empty] | Input to Architecture Workshop 10–11 Aug | bar: 2026-07-29 to 2026-08-10
| Track 2 | PRE-WORKSHOP: Draft integration patterns and API candidates | Architect | Draft integration approach doc | [20 empty] | Reviewed and agreed at Workshop 2.1 | bar: 2026-08-05 to 2026-08-13
| Track 2 | PRE-WORKSHOP: Prepare architecture open items list | Architect | Architecture open-items list for workshop | [20 empty] | Bain Architect (Sandeep) to review before Workshop 2.1 | bar: 2026-08-12 to 2026-08-17
| Track 2 | Architecture blueprint (solution, data, integration, AI/agent) | Architect | Architecture blueprint v1 (for Bain Architecture review) | [20 empty] | Bain Architecture written sign-off required before build | bar: 2026-07-29 to 2026-08-17
| Track 2 | Calculation data-package schema | Architect | Agreed schema; ADR signed | [20 empty] | Unblocks contract-first parallel build | bar: 2026-07-29 to 2026-08-06
| Track 2 | Bounded agent contracts (all 7 agents) | Architect | Agent contracts: inputs, outputs, failure modes, eval criteria | [20 empty] | Not in SN Gantt — required SOW deliverable | bar: 2026-08-05 to 2026-08-13
| Track 2 | Wave-1 data-source mapping | Lead FS | Data source map: scope, access owner, quality bar per source | bar: 2026-08-05 to 2026-08-17
| Track 2 | Architecture Decision Records (ADRs) | Architect | ADR per load-bearing decision (schema, VCC, retrieval etc.) | [20 empty] | Living doc; updated throughout Discovery
| Workshop | WORKSHOP 2.1: Architecture (2 days, TBD) | Bain Architects + SN Tech Leads | Target architecture agreed; guiding principles; integration patterns | [20 empty] | On-site: Sandeep, Siva ¦ Bain Solution & Data Architects, Dean, BCN Tech | bar: 2026-08-12 to 2026-08-13
| Workshop | WORKSHOP 2.2: Tech Design (3 days, TBD) | Bain Tech + SN Tech Leads | App design agreed; data model; integration interfaces; backlog items | [20 empty] | On-site: Sandeep, Siva ¦ Dean + BCN Tech | bar: 2026-08-14 to 2026-08-18
TRACK 3 · EXPERIENCE / UX Lead Full Stack Engineer + Bain Designer (Sam Taylor) | bar: 2026-08-24 to 2026-08-25
| Track 3 | UX discovery, wireframes and prototype (in progress) | Bain Designer | Prototype iterating based on user interviews | [20 empty] | User interviews ongoing — prototype not yet finalised | bar: 2026-07-29 to 2026-08-10
| Track 3 | PRE-WORKSHOP: Prepare prototype walkthrough for Workshop 1 | Bain Designer | Prototype demo script; screen walkthrough | [20 empty] | To be presented at Business Kick-off Workshop 4–6 Aug | bar: 2026-08-12 to 2026-08-17
| Track 3 | Build UX design for MVP (from prototype) | FE + Bain Designer | Mid-to-high fidelity designs; Figma files | [20 empty] | Builds on existing prototype — no redesign needed | bar: 2026-08-12 to 2026-08-20
| Track 3 | Designer-to-FE handoff process agreed | FE | Handoff doc; agreed Figma-to-FE process | [20 empty] | Mandhir confirmed this is a Discovery deliverable | bar: 2026-08-19 to 2026-08-25
TRACK 4 · QUALITY AND EVALUATION Senior QA/Eval Engineer | bar: 2026-08-24 to 2026-08-25
| Track 4 | Test strategy | QA/Eval | Test strategy doc | bar: 2026-07-29 to 2026-08-06
| Track 4 | Test case preparation | QA/Eval | Test cases per MVP capability | bar: 2026-08-05 to 2026-08-25
| Track 4 | Retrieval-quality eval definitions | QA/Eval | Eval definitions doc (agreed with Bain KM) | [20 empty] | Bain KM input required | bar: 2026-08-05 to 2026-08-17
| Track 4 | Eval harness scaffold | QA/Eval | Retrieval eval harness + baseline metrics vs. Glean | [20 empty] | Canonical questions from Bain KM needed | bar: 2026-08-12 to 2026-08-20
TRACK 5 · ENVIRONMENT AND STANDARDS Lead Full Stack Engineer | bar: 2026-08-24 to 2026-08-25
| Track 5 | PRE-WORKSHOP: Git, Jira, Confluence, Figma, Miro setup confirmed | Lead FS + Bain IT | All collaboration tools live; access confirmed | [20 empty] | Pre-requisite per workshop plan — must be done before Workshop 1 | bar: 2026-07-29 to 2026-08-06
| Track 5 | Dev environment setup (Bain-managed, Azure) | Lead FS | Dev environment live; access confirmed | [20 empty] | Bain IT to confirm Azure provisioning | bar: 2026-07-29 to 2026-08-17
| Track 5 | CI/CD and engineering standards | Lead FS | CI/CD pipeline; agreed coding standards doc | bar: 2026-08-05 to 2026-08-17
TRACK 6 · SECURITY AND RISK AI Agent Architect, Engagement Lead, AI-Native Functional Consultant | bar: 2026-08-24
| Track 6 | VRA scope + data classification | Architect | VRA scope doc; data classification framework | [20 empty] | Parallel to build — not back-loaded | bar: 2026-07-29 to 2026-08-17
| Track 6 | Risk / legal guardrail thresholds | EL + FC | Guardrail thresholds doc (named-person, defamation, CoI) | [20 empty] | Bain Legal input required | bar: 2026-08-05 to 2026-08-17
| Track 6 | RAID Log (maintained throughout) | EL | RAID Log v1 — reviewed weekly with Bain Tech Lead | [20 empty] | Living doc; reviewed at weekly governance cadence
| Track 6 | Assumptions log | EL | All build assumptions documented and tracked | [20 empty] | SN EL to drive per Mandhir confirmation
| Track 6 | Decision Rights Matrix | EL | Decision Rights Matrix — agreed by both parties | bar: 2026-08-12 to 2026-08-25
| Track 6 | Resource + team recommendation for MVP Build | EL | Team size, seniority, ramp-up plan | [20 empty] | Required for Discovery completion gate | bar: 2026-08-19 to 2026-08-25
SOW CONTRACTUAL GATES — per signed SOW, not optional | bar: 2026-08-24
| Contractual | PoC list agreed in writing (Bain + SN) | Joint | Signed PoC list | [20 empty] | ⚠ SOW hard deadline: end of Week 2 | bar: 2026-08-05 to 2026-08-06
| Contractual | PoC findings documented | SN EL | PoC findings report (findings, risks, recommended approach) | [20 empty] | ⚠ SOW hard deadline: end of Week 3 — confirm with Sandeep | bar: 2026-08-12 to 2026-08-19
EXIT GATE · Discovery sign-off + CoE gate — all items required in writing before build commences
☐ MVP scope agreed in writing — Bain PM + Bain Tech Lead
☐ Product backlog estimated with story points — accepted by Bain PM
☐ Solution architecture approved — Bain Architecture (written, within 5 business days)
☐ Technical risks documented in RAID Log — accepted by Bain Tech Lead
☐ Implementation approach agreed — Bain PM + Bain Tech Lead
☐ Delivery Recommendation accepted — Bain Steering Committee
LEGEND | bar: 2026-08-24 to 2026-08-25
✓ Completed — no action required
Active track activity (SN-owned, in progress)
Pre-workshop preparation activity
Workshop milestone
Bain input required — delays here delay Discovery
SOW contractual deadline (non-negotiable)
Discovery exit gate condition
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This needs to be kicked off ASAP
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Engagement Lead + Functional Consultant