## Slide 1
Sprint 2 at a glance
Delivery items only — epics are excluded and tracked at programme level
45
Committed at
sprint start
Sprint 1: 22
13
Added after
sprint started
Sprint 1: 28
48
Completed
(of 58 items)
Sprint 1: 22
83%
Completion
rate
Sprint 1: 44%
Reading the numbers
Scope grew by 13 items during the sprint, roughly 29% — down from 127% in Sprint 1.
Of the 45 items committed at the start, 36 completed. 9 carried into Sprint 3, plus 1 late-added QA item: 10 in total, now largely completed.
12 of the 13 added items were completed in the sprint, so unplanned work no longer displaced the plan.
Most of the Sprint 1 carryover closed, including the data foundation items and both think-cell reviews. Three data foundation items were moved to the general backlog.
Estimates were still not in Jira, so issue count is again the only measure. Hours are being captured from Sprint 3.
What the 13 added items were
5
Build and platform
Dashboard and target setup screens, Case Service, search API, taxonomy migration
4
Quality and testing
CI checks on every pull request, framework gap analysis, grammar and agent QA
2
Data and taxonomy
Parquet regeneration, move from test fixtures to live data
2
Demo readiness and feasibility
Full stack deployed to a demo environment, MS Foundry agent setup

## Slide 2
What Sprint 2 delivered
48 completed items, described by the part of the consultant journey they support
Choosing the peer set
9 items
Journey step: peer selection
Peer set screen to add, remove and adjust peers
AI agents propose a peer set and explain why
Sector detection and taxonomy classification
Comparability and confidence scoring
Opening any number
7 items
Journey step: evidence and audit trail
Every figure shows its source in four parts
Reported, adjusted or estimated — and why
Reconciliation and sanity checks on the data
Tamper-evident audit trail and log tab
Dashboard and setup
6 items
Journey steps: dashboard and target setup
Dashboard and target setup screens built
Target setup connected to the back end
Live run progress shown on screen
Engagement intent carried through the journey
Data foundations
8 items
Behind the scenes: data and taxonomy
Core data access and engine skeleton
End-to-end data map for the Opportunity Case
Search moved to the new Bain taxonomy
Bain source connectors, China and HK access
Platform and AI
10 items
Behind the scenes: services and agents
Per-case access control for every user
Secure service-to-service identity
Model gateway with safety controls
Full stack running in a demo environment
Quality and reviews
8 items
Behind the scenes: engineering practice
Automated checks on every code change
Testing gaps assessed and closed
think-cell and Andromeda assessments closed
Technology choices documented
Carried into Sprint 3
10 items · largely completed since
✓
Largely closed
Most of the carryover has been completed in the first half of Sprint 3
–
No longer a dependency
LSEG and CapIQ access and vendor rate limits: the GLS journey runs on the golden data set
!
Main open constraint
Development platform and agent access, granted on the dev environment only on Fri 2 Oct
Peer set selection now runs end to end, and every number it produces can be traced back to its source.

## Slide 3
Revised plan to the Global Leadership Summit
The go/no-go decision now sits in the middle of Sprint 4, one week before GLS on 26 October
31 Aug
14 Sep
28 Sep
12 Oct
19 Oct
26 Oct
6 Nov
Initial plan
5 sprints · 10 weeks
Revised plan
3½ sprints to go/no-go
S1 Foundations
S2 Peers & evidence
S3 Calculations
S4 Analysis & output
S5 Hardening & rehearsal
S1 Done
S2 Done
S3 Scope adjusted
S4 build
GLS readiness
No sprint before GLS
Today
Go / no-go
GLS
Initial plan
Five two-week sprints to 6 November, with code complete at the end of Sprint 4 and a full hardening and rehearsal sprint before the event.
Revised plan
Build runs to the go/no-go decision in the middle of Sprint 4, one week before GLS. The second half of Sprint 4 becomes GLS readiness, and there is no separate hardening sprint.
What it means for scope
Roughly one and a half sprints of time are gone, so Sprint 3 and Sprint 4 scope has been adjusted to the new timeline and the GLS scope cut aggressively. The cuts are on the next slide.
Where we are: midway through Sprint 3. Sprints 1 and 2 are delivered and the Sprint 2 carryover is largely closed. The go/no-go decision is now roughly two weeks away.

## Slide 4
Adjusting the GLS scope to the revised timeline
What is driving the pressure on the plan, and what changes in what we show at GLS
What is driving the pressure
Timeline brought forward
The go/no-go decision moved to the middle of Sprint 4, one week before GLS. That leaves three and a half sprints of build rather than five, with no hardening sprint.
Late access to the development platform and agents
Access was granted on the development environment only on Friday 2 October. Document fetching and document parsing depend on it, so that is where the main delay sits.
External data access is no longer a risk
The GLS journey runs on the golden data set, so LSEG, CapIQ and vendor rate limits are no longer dependencies for GLS.
What changes for GLS
01
Chat interface reduced
The chat will focus on interaction with the analysis rather than making changes to the data.
02
Full journey for the golden data set only
Consultants can run the entire journey for the golden data set companies provided by the BCN team. Other companies remain searchable, but the full journey will not run for them.
03
Further adjustments, raised early
Any other topics that put the timeline at risk will be identified and communicated as they come up before GLS.
The go/no-go decision one week before GLS will be taken against this reduced scope.