## Slide 1
Sprint 3 at a glance
Delivery items only — epics are excluded and tracked at programme level
28
Committed at
sprint start
Sprint 2: 45
5
Added after
sprint started
Sprint 2: 13
27
Completed
(of 33 items)
Sprint 2: 48
82%
Completion
rate
Sprint 2: 83%
Reading the numbers
27 of 33 items completed. Of the 28 committed at the start, 22 finished and 6 carry into Sprint 4.
Only 5 items were added after the sprint began, a scope increase of about 18%, down from 29% in Sprint 2. All 5 were completed.
The think-cell licence, BAP deployment and similar tasks were removed from the sprint, as they are not a dependency for GLS.
The analysis screen, planned as a stretch goal, was partially delivered ahead of plan.
What the 5 added items were
2
Screens and evidence
Peer enrichment and error screens; source list API for the evidence view
2
Platform and design
Full stack deployment with infrastructure as code; AI search design
1
Defect fix
Peer curation timing out on serial calls to MS Foundry

## Slide 2
What Sprint 3 delivered
27 completed items, described by the part of the consultant journey they support
Case for Change
5 items
Journey step: Case for Change
Case for Change screen built
Calculation engine for the GLS scope
Golden data set curated and loaded
Analysis and chat
5 items
Journey steps: analysis and assistant
Analysis screen foundations, ahead of plan
Chat and its tool catalogue
Logs and sources tab on every case
AI agents
4 items
Behind the scenes: agents
Narrative agent writes the story
Chat assistant agent
Peer selection agent improved
Peer curation timeout fixed
Services and platform
7 items
Behind the scenes: services
Audit service and document upload
Full stack deployed with infrastructure as code
Security scan framework
AI search design, ADRs
Quality and testing
6 items
Behind the scenes: engineering practice
Frontend contract and boundary tests
Peer selection agents tested
Audit, BFF and Case services tested
Ranking, sourcing and merge logic checked
Ahead of plan
The analysis screen was a stretch goal for Sprint 3 and is almost done. That frees Sprint 4 to focus on the output screen, which the go/no-go also depends on.

## Slide 3
Where we are against the plan to GLS
Sprint 3 is complete and Sprint 4 started on 12 October; the go/no-go decision is one week away
31 Aug
14 Sep
28 Sep
12 Oct
19 Oct
26 Oct
6 Nov
Initial plan
4 sprints of build
GLS at end of Sprint 4
Revised plan
3½ sprints of build
Go/no-go 1 week pre-GLS
S1 Foundations
S2 Peers & evidence
S3 Calculations
S4 Analysis & Output
S5 Support and Hardening
S1 Done
S2 Done
S3 Done
S4 accelerated
Stabilise for GLS
S5 Support and Hardening
!
Today
Go / no-go
GLS
Done: Sprints 1 to 3
Sign-in, company search, peer selection with evidence, the Case for Change, the calculation engine for the GLS scope, and the analysis screen foundations ahead of plan.
Now: Sprint 4, week 1
The full journey for the golden data set companies, from target setup to output, working end to end for the go/no-go decision in the week of 19 October.
Next: week 2 and GLS
Stabilise the version chosen at go/no-go, finish the remaining output slides, test with Bain users and rehearse for GLS on 26 October.
The plan holds: Sprints 1 to 3 are delivered on the revised timeline. The trade-off stands: one week less development in exchange for a go/no-go decision a week before GLS and no last-minute deployments.

## Slide 4
Sprint 4 is accelerated to be ready for go/no-go
Work planned across two weeks has been brought into one, so the full journey can be shown in the week of 19 October
Initial Sprint 4
Revised Sprint 4
Analysis, output and assistant built across two weeks · code complete 23 Oct
Week 1 · analysis, output and chat ready by 16 Oct
Week 2 · stabilise for GLS
Go / no-go w/c 19 Oct
Analysis screen
Brought forward to week 1
Levers with cost bars, uplift and size of prize
Override uplift % or size of prize per lever
Figures recalculate when peers change
Recommendations from the golden data set
Output screen
Brought forward to week 1
Bain-formatted output generated from the case
Title, summary, peer set and lever slides
Regenerate after changes, then download
Reflects peer changes and overrides
Chat on each screen
Brought forward to week 1
Answers questions about the figures, with sources
Explains the method, peers and comparability
Read-only: points to on-screen controls for changes
Available on the analysis and output screens
The heaviest sprint so far: Sprint 4 starts with 58 committed items, against 28 in Sprint 3, 45 in Sprint 2 and 22 in Sprint 1, and most of them must be working by the go/no-go decision at the end of week 1.