## Slide 1
OPPORTUNITY CATALYST
Sprint 3 Retrospective
Case for Change and calculations — the Case for Change screen, the GLS calculation engine and the golden data set
28 September – 12 October 2026 · OI3 board · 33 delivery items in sprint at close
Notes: Source: Jira Sprint Report and burndown (original time estimate), OI3 board, sprint 49544. Three epics (OI3-157, OI3-244, OI3-246) are excluded from all counts and tracked at programme level. Jira issue keys remain OI3 following the rename to Opportunity Catalyst.

## Slide 2
Sprint 3 at a glance
28
Committed at
sprint start
5
Added after
sprint started
27
Completed
(of 33 items)
82%
Completion
rate
Reading the numbers
27 of 33 items completed. Of the 28 committed at the start, 22 finished and 6 carry into Sprint 4.
5 items were added after the sprint began, a scope increase of about 18%, down from 29% in Sprint 2. All 5 were completed within the sprint.
The think-cell licence, BAP deployment and similar tasks were removed from the sprint, as they are not a dependency for GLS.
Hours were recorded in Jira for the first time, about 450 at the start of the sprint, so the burndown is now measured in hours. Issue count is no longer the only measure.
What the 5 added items were
Screens and evidence
2
Peer enrichment and error screen, source list API for the evidence view
Platform and design
2
Full stack deployment with infrastructure as code, AI search design
Defect fix
1
Peer curation timing out on serial calls to MS Foundry
Opportunity Catalyst | Sprint 3 Retrospective
2

## Slide 3
Sprint 2 compared with Sprint 3
Both sprints counted on the same basis — delivery items only, epics excluded
Items completed
Sprint 2
48
Sprint 3
27
fewer, larger items
Completion rate
Sprint 2
83%
Sprint 3
82%
level, down 1 point
Scope added mid-sprint
Sprint 2
29%
Sprint 3
18%
down from 13 items to 5
Items carried over
Sprint 2
10
Sprint 3
6
down by 4 items
What changed between the two sprints
Fewer items, now sized in hours
Sprint 3 committed to 28 items against 45 and finished 22. It is the first sprint with hours in Jira, about 450, so item counts are no longer the only measure.
Additions were fully absorbed
All 5 items added mid-sprint completed in the same sprint. In Sprint 2, 12 of 13 did.
External blockers cleared
No item ended the sprint blocked on a vendor, against two in Sprint 2. The golden data set removes the LSEG and CapIQ dependencies for GLS.
Opportunity Catalyst | Sprint 3 Retrospective
3

## Slide 4
Burn profile
Hours from the Jira burndown (original time estimate), the first sprint with estimates recorded. Values are read from the chart and rounded.
Chart: Hours remaining
| Sep 28 | Sep 29 | Sep 30 | Oct 1 | Oct 2 | Oct 5 | Oct 6 | Oct 7 | Oct 8 | Oct 9 | Oct 12
Remaining (actual) | 452 | 457 | 461 | 470 | 422 | 413 | 413 | 410 | 365 | 305 | 79
Guideline (ideal) | 452 | 406.8 | 361.6 | 316.4 | 271.2 | 226 | 180.8 | 135.6 | 90.4 | 45.2 | 0
Sep 28 – Oct 1
Scope rises before it falls
The line opens at about 450 hours and climbs to around 485 on 1 October as work is added. Nothing burns down in the first four days.
Oct 2 – 9
A slow decline once access arrives
Platform and agent access is granted on 2 October. Remaining work falls from about 470 to 305 hours over the next six working days, still far above the guideline.
Oct 12
Most of the closure lands on the final day
Remaining falls from about 305 to 80 hours on the last day: around 225 hours, roughly 60% of the sprint's burn, reach Done at close.
Opportunity Catalyst | Sprint 3 Retrospective
4

## Slide 5
How sprint scope changed
Chart: 
| Committed at start | Added mid-sprint
Completed | 22 | 5
Carried over | 6 | 0
Every addition was completed
All 5 items added mid-sprint were done before the sprint closed, against 12 of 13 in Sprint 2.
Additions were follow-on work and one fix
The peer enrichment and error screen, source list API, full stack deployment and AI search design follow from work in the sprint. The fifth fixed a peer curation timeout.
Tasks not needed for GLS were removed
The think-cell licence, BAP deployment and similar tasks were taken out of the sprint rather than completed, as they are not a dependency for GLS.
Opportunity Catalyst | Sprint 3 Retrospective
5

## Slide 6
Status of the 6 spillover items
Five of the six are under way or in review, and none is blocked on an external party
Chart: 
| To Do | In Progress | In Review | Blocked
Items | 1 | 4 | 1 | 0
Reading the carryover
OI3-221, the confirm peers API, is in progress. It joins peer selection to the Case for Change end to end and is the key item for go/no-go.
Three more are in progress: OI3-215 the data sources sheet, OI3-230 QA for the peer service, and OI3-48 development environment and access.
One is in review: OI3-21 security and governance, now open for a third sprint.
One had not started: OI3-227, QA for the peer selection screen. By 13 October it was in progress and OI3-230 had moved to review.
Opportunity Catalyst | Sprint 3 Retrospective
6

## Slide 7
What Sprint 3 delivered
27 completed items, grouped by the part of the user journey they support
Case for Change
5 items
Journey step: Case for Change
Case for Change screen built
Calculation engine logic agreed for the GLS scope
GLS calculation engine built
Golden data set curated with BCN
Golden data set delivered in JSON
Analysis and chat
5 items
Journey steps: analysis and assistant
Analysis screen foundations, ahead of plan
Chat and its tool catalogue (CopilotKit / AG-UI)
Logs and sources tab on every case
Source list API behind the evidence view
Peer enrichment and error screens
AI agents
4 items
Journey steps: narrative and assistant
Narrative agent that writes the story
Chat assistant agent
Peer selection agent improvements
Peer curation timeout fixed
Services
3 items
Behind the scenes: case services
Audit service processing events from the service bus
Document upload API
Rate and quota management
Platform and architecture
4 items
Behind the scenes: platform and design
Full stack deployed with infrastructure as code
Security scan framework, run on demand
Architecture decision records logged
AI search design document
Quality and testing
6 items
Behind the scenes: engineering practice
Frontend contract and network boundary tests
Peer selection agents: ranking, sourcing and merge logic
Audit service and Experience BFF tested
Case Service tested
The Case for Change now runs on the golden data set, and the analysis screen and chat start Sprint 4 with a head start.
Opportunity Catalyst | Sprint 3 Retrospective
7

## Slide 8
Factors behind the spillover and items to watch
Five points carried into Sprint 4, each with a clear next step
01
Platform and agent access arrived mid-sprint
Access to the development platform and the AI agents, which document fetching and parsing depend on, was granted on the development environment only on 2 October. Dependent work started late, and around 60% of the sprint's hours closed on the final day.
02
Two items have now carried through three sprints
OI3-21 security and governance and OI3-48 development environment and access have been open since Sprint 1. The other three from Sprint 2's list closed or were removed. Each remaining item needs a named owner and a date, or a decision to close it.
03
The link from peers to the Case for Change is still open
OI3-221, the confirm peers API, carries into Sprint 4. The go/no-go journey depends on it, so it needs to close in the first days of the sprint.
04
Team capacity remains the main constraint
No data engineer was onboarded for the GLS sprints, and the full-stack developer due in Sprint 2 could not contribute for a full sprint. The golden data set offsets the first, but not connecting live sources narrows the GLS functionality.
05
Sprint 4 carries the heaviest load so far
Sprint 3 burned about 370 hours over two weeks. Sprint 4 starts with 58 items, most needed by go/no-go after one week, so its estimated hours should be checked against that rate now.
Opportunity Catalyst | Sprint 3 Retrospective
8

## Slide 9
Retro board
What went well
82% completion, level with Sprint 2
All 5 mid-sprint additions completed
Case for Change screen and GLS calculation engine delivered
Golden data set curated and loaded
Analysis screen and chat started ahead of plan
First sprint with hour estimates in Jira
What to improve
Platform and agent access granted only on 2 October
Around 60% of the tasks closed on the final day
No burn-down in the first four days
Two items open since Sprint 1
Confirm peers API not finished
What to try next
Close OI3-221 in the first days of Sprint 4
Owner and date, or close, for OI3-21 and OI3-48
Move items to Done as they finish, not at close
Keep estimates current as Sprint 4 scope changes
Opportunity Catalyst | Sprint 3 Retrospective
9