## Slide 1
OPPORTUNITY CATALYST
Sprint 2 Retrospective
Peers and evidence — peer set selection, the evidence trail and the first screens
15 – 27 September 2026 · OI3 board · 58 delivery items in sprint at close
Notes: Source: Jira Sprint Report, OI3 board, sprint 49388. One epic (OI3-157) is excluded from all counts and tracked at programme level. Jira issue keys remain OI3 following the rename to Opportunity Catalyst.

## Slide 2
Sprint 2 at a glance
45
Committed at
sprint start
13
Added after
sprint started
48
Completed
(of 58 items)
83%
Completion
rate
Reading the numbers
48 of 58 items completed. Of the 45 committed at the start, 36 finished and 9 carry into Sprint 3.
13 items were added after the sprint began, a scope increase of roughly 29%. 12 of those 13 were completed within the sprint.
Much of the Sprint 1 carryover closed here, including the data foundation items OI3-37, 39, 42 and 45 and the two think-cell reviews.
Estimates were still not recorded in Jira. The team estimated in hours, the board was configured for story points, and capturing them required admin access. Issue count remained the only available measure. Fixed starting from Sprint 3.
What the 13 added items were
Build and platform
5
Dashboard and target setup screens, Case Service, search API and taxonomy migration
Quality and testing
4
CI checks on every PR, framework gap analysis, grammar and agent QA
Data and taxonomy
2
Parquet regeneration, fixtures-to-live migration
Demo readiness and feasibility
2
Full stack deployed via Bastion, MS Foundry agent setup
Opportunity Catalyst | Sprint 2 Retrospective
2

## Slide 3
Sprint 1 compared with Sprint 2
Both sprints counted on the same basis — delivery items only, epics excluded
Items completed
Sprint 1
22
Sprint 2
48
more than doubled
Completion rate
Sprint 1
44%
Sprint 2
83%
up 39 points
Scope added mid-sprint
Sprint 1
127%
Sprint 2
29%
down from 28 items to 13
Items carried over
Sprint 1
28
Sprint 2
10
down by 18 items
What changed between the two sprints
Twice the commitment, and it held
Sprint 2 committed to 45 items against 22 in Sprint 1, and finished 36 of them. Sprint 1 finished 9 of its 22.
Additions stopped becoming carryover
12 of the 13 items added mid-sprint completed in the same sprint. In Sprint 1, 15 of 28 additions carried over.
The Sprint 1 backlog largely cleared
The items still open are mostly the same long-running access and dependency items, not new work.
Opportunity Catalyst | Sprint 2 Retrospective
3

## Slide 4
Burn profile
Issue count from the Jira burndown. The chart counts the one epic and the three later-removed items, so it opens at 49 rather than 45.
Chart: Issue count
| Sep 15 | Sep 16 | Sep 17 | Sep 18 | Sep 21 | Sep 22 | Sep 23 | Sep 24 | Sep 25 | Sep 27
Remaining (actual) | 49 | 48 | 46 | 43 | 43 | 42 | 42 | 38 | 36 | 11
Guideline (ideal) | 49 | 43.56 | 38.11 | 32.67 | 27.22 | 21.78 | 16.33 | 10.89 | 5.44 | 0
Sep 15 – 18
Scope rises before it falls
The line opens at 49 and steps above it twice, to around 52, as items are added in the first three days. It stays well above the guideline throughout the first week.
Sep 21 – 25
A gradual decline through week two
Remaining work falls from 43 to 36 across the second week — real progress, but at a rate that leaves most of the sprint still open on the final Friday.
Sep 25 – 27
Over half the closure lands at the end
Remaining falls from 36 to 11 in the closing days: around 25 items, more than half the sprint's output, reach Done once AI platform access arrives.
Opportunity Catalyst | Sprint 2 Retrospective
4

## Slide 5
How sprint scope changed
Chart: 
| Committed at start | Added mid-sprint
Completed | 36 | 12
Carried over | 9 | 1
Additions were absorbed, not deferred
12 of the 13 items added mid-sprint completed before the sprint closed. Only OI3-194, a QA item, carried over.
Most additions were planned follow-on work
The dashboard and target setup screens, Case Service and the taxonomy migration follow directly from work already in the sprint.
Three items were removed from the sprint
OI3-18, 43 and 65 — all data foundation items — were taken out rather than completed, and put into the general backlog, as they are not specific to any of the Sprints.
Opportunity Catalyst | Sprint 2 Retrospective
5

## Slide 6
Status of the 10 spillover items
Seven of the ten are already under way, in review, or blocked on an external party rather than unstarted
Chart: 
| To Do | In Progress | In Review | Blocked
Items | 3 | 3 | 2 | 2
Reading the carryover
Two items are blocked: OI3-82 rate and quota management, and OI3-147 the Data Access Service. Both wait on vendor limits being confirmed.
Two are in review — OI3-21 security and governance and OI3-27 architecture decision records — waiting on review capacity, not build effort.
Three are in progress: development environment and access, the think-cell licence, and the LSEG and CapIQ rate limits.
Three have not started: the peer candidate knowledge base, frontend boundary tests, and one QA item added late in the sprint.
Opportunity Catalyst | Sprint 2 Retrospective
6

## Slide 7
What Sprint 2 delivered
48 completed items, grouped by the part of the user journey they support
Peer set selection
9 items
Journey step: peer selection
Peer set screen, with add, remove and adjust
Agents that propose a peer set and explain it
Sector detection and taxonomy classification
Universe scoping, long list and peer enrichment
Comparability assessment and confidence scoring
Evidence and audit trail
7 items
Journey step: opening any number
Evidence service and the claim contract
Four-part source audit behind each figure
Metric acquisition and origin classification
Reconciliation, imputation and sanity control
Tamper-evident audit trail and log tab
Screens and journey
6 items
Journey steps: dashboard and target setup
Dashboard screen and target setup screen
Target setup API wired to the screen
Live run progress streamed back to the screen
Engagement intent carried through the journey
Data foundations
8 items
Behind the scenes: data and taxonomy
Core data access and calculation engine skeleton
End-to-end data map for the Opportunity Case
Search API migrated to the new Bain taxonomy
Bain source connectors, China and HK access
Platform, identity and AI
10 items
Behind the scenes: services and agents
Experience BFF with per-case entitlement
Service-to-service identity and event transport
Case Service and model gateway with safety controls
Full stack deployed to a demo environment
Quality and reviews
8 items
Behind the scenes: engineering practice
Test frameworks and CI checks on every pull request
Framework gap analysis and testing improvements
think-cell and Andromeda assessments closed
Technology choices documented with reasoning
The peer set journey step now runs end to end, and every number it produces can be traced back to its source.
Opportunity Catalyst | Sprint 2 Retrospective
7

## Slide 8
Factors behind the spillover and items to watch
Five points carried into Sprint 3, each with a clear next step
01
AI platform access arrived on the final day of the sprint
Access to the AI platform services the peer selection cycle depends on — AI Search and document parsing — was granted to the team only on the last day of Sprint 2. Until then the full cycle could not be completed end to end, and the work that depends on it could not be finished or tested within the sprint.
02
Five items have now carried through two sprints
OI3-21 security and governance, OI3-27 architecture decision records, OI3-48 development environment and access, OI3-54 think-cell licence and OI3-82 rate and quota management have been open since Sprint 1. Each needs a named owner and a date, or a decision to close it.
03
External dependencies remain the main constraint
The two blocked items and the LSEG and CapIQ rate limits all wait on a party outside the team. The Sprint 3 plan carries the same dependencies through its client asks list.
04
Three data foundation items were removed from the sprint
OI3-18, OI3-43 and OI3-65 left the sprint rather than completing. These now sit on the general backlog, but still require close follow-up to not to become another blocker for the GLS scope.
05
Estimates are being captured in Jira from Sprint 3
Sprint 2 ran without estimates in Jira, so issue count is again the only measure. Hours are being entered on the Sprint 3 items before the sprint starts, which makes the burndown and velocity reports usable from that point.
Opportunity Catalyst | Sprint 2 Retrospective
8

## Slide 9
Retro board
What went well
48 items completed, against 22 in Sprint 1
36 of 45 committed items delivered
Peer set journey step now works end to end
Evidence and audit trail delivered alongside it
12 of 13 mid-sprint additions still completed
Most Sprint 1 carryover closed, including the data foundations
What to improve
AI platform access (AI Search, document parsing) granted only on the last day
Over half the sprint's closure landed in the final days
Five items have been open since Sprint 1
Two items ended the sprint blocked on vendors
Three data foundation items were removed, not finished
No estimates in Jira for a second sprint
What to try next
Raise platform access requests a sprint ahead of the work
Set a date or close decision for each two-sprint item
Escalate vendor rate and quota limits as one ask
Confirm where the three removed items now sit
Keep estimates in Jira before Sprint 3 starts
Opportunity Catalyst | Sprint 2 Retrospective
9