## Slide 1
OC 3.0
Sprint 1 Retrospective
Foundations — first 3 screens, database preparation, APIs, AI scaffolding
1 – 14 September 2026 · OC3 board · 50 delivery items in sprint at close
Notes: Source: Jira Sprint Report and Burndown Chart, OC3 board, sprint 49272. Epics excluded from all counts.

## Slide 2
Sprint 1 at a glance
Delivery items only — the 11 epics carried on the board are excluded and tracked at programme level
22
Committed at
sprint start
28
Added after
sprint started
22
Completed
(of 50 items)
44%
Completion
rate
Reading the numbers
The sprint closed with 28 more items than it opened with — scope grew by roughly 127% during the sprint.
Of the 22 items committed at the start, 9 completed. The remaining 13 carry into Sprint 2.
13 of the 22 completed items were added after the sprint began, so a meaningful share of capacity went to unplanned work.
The team estimated Sprint 1 in hours, but the board is configured for story points and capturing those estimates in Jira requires admin access, so no estimates appear in the report. Issue count is therefore the only available measure here, and item sizes vary considerably.
OC 3.0 | Sprint 1 Retrospective
2

## Slide 3
How sprint scope changed
Items marked with an asterisk in the Jira sprint report entered the sprint after the start time
Chart: 
| Committed at start | Added mid-sprint
Completed | 9 | 13
Carried over | 13 | 15
Both halves are similar in size
The 28 items added mid-sprint are close in volume to the 22 originally committed, spanning frontend, integration and calculation-engine work.
Added work did progress
13 of the 28 additions completed within the sprint, a similar rate to the committed items.
Committed items carried over
13 of the original 22 remain open, including the data foundation items OC3-18, 42, 43 and 45.
OC 3.0 | Sprint 1 Retrospective
3

## Slide 4
Burndown profile
Reconstructed from the Jira burndown chart, which counts epics as well — verify exact daily values before circulating externally
Chart: Issue count
| Sep 1 | Sep 2 | Sep 3 | Sep 4 | Sep 5 | Sep 6 | Sep 7 | Sep 8 | Sep 9 | Sep 10 | Sep 11 | Sep 12 | Sep 13 | Sep 14
Remaining (actual) | 49 | 46 | 46 | 47 | 46 | 46 | 46 | 45 | 43 | 43 | 41 | 38 | 37 | 37
Guideline (ideal) | 25 | 23.077 | 21.154 | 19.231 | 17.308 | 15.385 | 13.462 | 11.538 | 9.615 | 7.692 | 5.769 | 3.846 | 1.923 | 0
Sep 1
Scope set above the guideline
The remaining line opens near 49 against a guideline starting at 25, so the sprint began carrying more than the guideline assumed.
Sep 1–6
Limited movement in week one
Few items reached Done in the first week. This aligns with the environment, access and feasibility work set out under main factors.
Sep 7–12
Most closure in the second half
The bulk of completions land after Sep 7 and level off near 37 remaining as the sprint ends.
OC 3.0 | Sprint 1 Retrospective
4

## Slide 5
Status of the 28 carryover items
Most carryover is already under way — 21 of the 28 are in progress, in review, or on hold rather than unstarted
Chart: 
| To Do | In Progress | In Review | On Hold / Blocked
Items | 7 | 9 | 7 | 5
Reading the carryover
9 items in progress represent active work with context already built, and should be first into Sprint 2.
7 items in review (OC3-15, 21, 27, 37, 39, 42, 88) are waiting on review capacity rather than build effort.
5 items are on hold or blocked, each tied to an external dependency.
7 items have not started. Most arrived mid-sprint with limited runway remaining.
OC 3.0 | Sprint 1 Retrospective
5

## Slide 6
What Sprint 1 delivered
22 completed items, grouped by the foundation they established
Frontend foundation
OC3-46 Application UI skeleton
OC3-69 App shell, routing and state
OC3-71 Bain-token library on Radix
OC3-56 Figma review
Platform & identity
OC3-61 Monorepo and service scaffolding
OC3-68 Experience BFF + Entra SSO
OC3-96 Agent skeleton with standards
OC3-53 Code sharing from existing projects
Data & search
OC3-44 Initial data ingestion / dump
OC3-77 Company search and disambiguation
OC3-55 Search API architecture and contracts
OC3-103 File archive for Glean + Snowflake
Architecture & quality
OC3-16 Integration architecture and APIs
OC3-47 Test and automation strategy
OC3-92 Technical swim lanes
OC3-95 Technical debt register published
The scaffolding the rest of the programme depends on is now in place.
OC 3.0 | Sprint 1 Retrospective
6

## Slide 7
Main factors behind the carryover
Four cross-cutting constraints absorbed capacity across the sprint, independent of individual item complexity
01
Developer environment migration (ongoing)
The development team is being moved off the VDI environment onto Bain laptops. The VDI is materially slower for development work. The migration began during Sprint 1 and is not yet complete, so it continues to affect Sprint 2.
02
Access provisioning
Access to Bain and Microsoft Azure systems, platforms and data sources was being provisioned in parallel with delivery. OC3-2 service provisioning and OC3-48 development environment and access remain open, and the dependency affected work beyond those items.
03
Additional requirements and feasibility assessment
Requirements surfaced during the sprint that had to be assessed for feasibility before they could be planned, including the Andromeda platform and think-cell. This assessment work was unplanned and sat with the same people delivering build items.
04
User journeys and design finalisation
User journeys and design elements were still being finalised against stakeholder feedback during the sprint, keeping frontend and data-requirement items such as OC3-37 and OC3-102 moving while build work was under way.
OC 3.0 | Sprint 1 Retrospective
7

## Slide 8
Retro board
Starters drawn from the sprint data — the team adds to each column during the session
What went well
Foundation layer landed: monorepo, SSO, app shell, component library
22 items completed despite a mid-sprint environment migration
Technical debt register published in Sprint 1
Architecture and swim lanes documented early
13 of 28 added items still completed
Team estimated the sprint, even though Jira could not record it
What to improve
Scope grew 127% after the start with no agreed gate
9 of 22 committed items completed
Environment and access work ran in parallel with delivery
Design and journey decisions arrived after build began
Unplanned feasibility work (Andromeda, think-cell) absorbed capacity
Hour-based estimates were not captured in Jira, so there is no baseline
What to try next
Get admin access to configure the board so estimates are captured
Track epics at programme level, not on the board
Name an owner and date for each dependency/blocker
Confirm journeys and designs ahead of the sprint they build in
Complete the laptop migration and close out access provisioning
OC 3.0 | Sprint 1 Retrospective
8